## Slide 1: STEP AP242 e2 AIA-ASD Collaboration 18th of October 2017
Project Coordination:
Jean Brange, Boost Conseil
Jean-Yves Delaunay, Airbus
Tom Bluhm, Boeing
Darla Nettles-Edwards, Liberty Business Associates

## Slide 2: AP242 ed2 plan and Key Interdependencies
DIS Ballot including ISO process
FDIS Ballot
ISO Deadline
12 Dec. 2017
4 July
29 Aug.
DIS Ballot resolution
12 + 8 Weeks
6,5 weeks
2 weeks
FDIS Ballot resolution
FDIS Ballot convener review
4 May
8 weeks
12 SEPT.
20 June
Sending of the IS
for publication to ISO
FDIS sent to ISO
SC 4 meeting
23 May
Harmonization
Finalization
PDES Inc
offsite
AP242 ED2
Core model V1
(P4000)
ISO /TC184 /SC 4
FDIS
Doc.
Prep.
4 weeks
Core Model
DIS Ballot
Incl. ISO process
Core model
Ballot resolution
2 weeks
CTCs harmonization
Core Model
DIS Ballot
Doc. prep
12 + 4 W
4 weeks
2 weeks
23 May
9 May
10 Jan
STEP extended Architecture
Core Model
NWI Ballot incl. Core model
NWI: 25 Oct. : before the ballot of the STEP Ext Archi.
2 months ballot: 25 Dec
DIS ballot start 25 Dec. : 4 month ;: 25 April

## Slide 3: Plan to deliver the AP242 e2 FDIS
End of DIS ballot resolution and of the technical work to introduce the core model: 20 May 2018
End of preparation of the FDIS technical documentation: 14 June 2018
Start of FDIS Ballot: 14 June
FDIS Ballot : 8 weeks
Risks
  AP242 e2 DIS ballot resolution
  Core model E1, including the AP239 e3 – AP242 e2 harmonization to be part as a technical annex

## Slide 4: Preparation in Q3 2018 of the whitepaper for STEP AP242 roadmap
Complete STEP Extended Architecture
Maintenance of STEPmod and SMRL
Industry Requirements
  Increasing need of the A&D industries for interoperability
  Integrated technological processes used in the 3D Model Based Definition
  Enhancements: PMI semantic, Composite design, mechanical features, holes and fastener, additive manufacturing, etc.
  New content: Tubing, etc.
Start of identification of gaps and enhancements, to be incorporated in the project plan for the STEP AP242 e3 project
Help needed: Industries to identify their priorities and resources for the development of STEP AP242 e3
Planning a whitepaper for Q2 – Q3 2018 as input for AP242 e3 New Work Item
  To be proposed to ISO for ballot before the end of 2018

## Slide 5: Issues and project risks (1/2)
CVS Source Forge stops on the 30th of Nov. 2017
Validation of the STEP Extended architecture
  Standing document CIB ballot planned to start in Jan. 2018
  Core model E1 attached in a technical annex (informative) of AP242 e2 FDIS
Limited resources
  Same persons used in multiples projects / activities

## Slide 6: Issues and project risks (2/2)
3 months to finalize the STEP AP242 e2 – AP239 e3 harmonization
Need an overall plan for the development, including the update of STEPmod and of the STEP lib, with the ballot of the Core Model e1 before the AP239 e3 DIS
Short period of time for the resolution of the AP242 E2 DIS comments
  Face to face meeting during the next PDES Inc offsite (12 – 16 March 2018)
  Face to face meeting before the ISO /TC 184 /SC 4 meeting in May 2018